## NAMS Budget
AIKEN COUNTY PUBLIC SCHOOLS
NAMS TOTAL PROJECT BUDGET WORKSHEET
|  |  |  | 06.14.23 | 2025-06-02
| Conceptual Estimate | Conceptual Estimate R1 | Conceptual Estimate R2 | SCHEMATIC DESIGN | SCHEMATIC DESIGN
HARD / CONSTRUCTION COSTS | 2017-11-16 | 2017-01-30 | 2017-02-14
Building Construction | 750000 | 400000 | 400000
New Construction (76,628 SF ($32m) @ $427 / SF) |  |  |  | 39842752 | 36178863 | (including 3% design contingency)
GC Bonds & Fees |  |  |  |  | 1496165
FFE - Equipment |  |  |  | 0 | 0
FFE - Playground |  |  |  | 0 | 0
IT / Security (Data Wiring, Access Controls, BDA, Security) |  |  |  | 0 | 0
Construction Sub-Total | 3500 | 400000 | 400000 | 39842752 | 37675028
Contingency (5%) | 175 | 20000 | 20000 | 1992137.6 | 1883751.4
TOTAL HARD / CONSTRUCTION COSTS | #REF! | #REF! | #REF! | 41834889.6 | 39558779.4
SOFT COSTS EQUIPMENT
Moving Expenses |  |  |  | 250000 | 250000
FFE - Furniture and Equipment (approx. 7%) |  |  |  | 2928442.272 | 2769114.558
Playgound |  |  |  |  | 0
Furniture Isolated |  |  |  |  | 0
IT / Security (TV's, Smartboards, Computers, Security) 3% of Construction | 0 | 0 | 0 | 1255046.688 | 1186763.382
ESTIMATED SOFT COSTS TOTAL | 0 | 0 | 0 | 4433488.96 | 4205877.94
PROFESSIONAL FEES
A/E Basic Services Professional Fees 6% of Construction | 50000 | 50000 | 50000 | 2173750 | 2274000
A/E Add Services (Landscape,Roof Consultant, Furniture Design and Procurement, Geotechnical, Survey) |  |  |  | 119450 | 139315
Design Team Reimbursables (mileage, travel, printing, etc) | 13000 | 13000 | 13000 | 17500 | 17500 | (not to exceed)
PROFESSIONAL FEES TOTAL | 50000 | 50000 | 50000 | 2310700 | 2430815
SURVEY AND TESTING FEES
Phase 1 Environmental Site Assessment |  |  |  | 4000 | 0
Testing and Special Inspections 1% of Construction | 13000 | 13000 | 13000 | 418348.896 | 395587.794
Impact and Tap Fees 0.5% of Construction |  |  |  | 209174.448 | 197793.897
SURVEY AND TESTING FEES | 13000 | 13000 | 13000 | 631523.344 | 593381.691
SUB-TOTAL | #REF! | #REF! | #REF! | 49210601.904 | 46788854.031
Owner Contingency ( |  |  |  | 1255046.688 | 2808164
SUB-TOTAL |  |  |  | 50465648.592 | 49597018.031
Escalation (to midpoint of constuction 12/25) |  |  |  | 2523282.4296 | 2402981.97
Total |  |  |  | 52988931.0216 | 52000000.001